## Slide 1
01
GIU · PROJECT MANAGEMENT · SPRING 2026
A Full Project Management Plan for
Campus Event
Management System.
PRESENTED BY
Ibrahim Madany
Project Manager
Yassin Kassem
Scrum Master
Loay Waleed
Product Owner
Malek Khaled
Risk Manager
Youssef Othman
Comms & QA Lead
INSTRUCTOR
Dr. Abdallah Osman · Introduction to Project Management
GIU / SPRING 26

## Slide 2
02
Campus Event Management System · Spring 2026 · GIU
§ 00 · CONTENTS
Five chapters. Five owners.
Each role presents one section of the plan, end to end.
01
Project Charter & Methodology
IBRAHIM MADANY · PROJECT MANAGER
02
Delivery & Sprints
YASSIN KASSEM · SCRUM MASTER
03
Product & Backlog
LOAY WALEED · PRODUCT OWNER
04
Risk Management
MALEK KHALED · RISK MANAGER
05
Stakeholders, QA & Closure
YOUSSEF OTHMAN · COMMS & QA LEAD

## Slide 3
03
Campus Event Management System · Spring 2026 · GIU
§ 01 · CHAPTER
PROJECT MANAGER
Ibrahim Madany
IN THIS SECTION
01
Project Charter — overview & objectives
02
Scope, assumptions & constraints
03
Methodology — why Agile, not Waterfall
04
Timeline & schedule baseline

## Slide 4
04
Campus Event Management System · Spring 2026 · GIU
IBRAHIM MADANY · PROJECT MANAGER
§ 01 · PROJECT CHARTER
One platform for every campus event.
Replacing scattered WhatsApp groups, posters, and email threads with a single source of truth.
OVERVIEW
A web platform that lets GIU students discover events, organizers manage registrations, and admins monitor engagement — delivered as an MVP across three sprints.
OBJECTIVES (SMART)
60%
Reduction in manual event-handling effort vs current workflow.
≥99%
RSVP success rate with strict capacity enforcement.
<1m
Notification delivery time, email + in-app combined.
3
Sprints to ship a working MVP for all five modules.

## Slide 5
05
Campus Event Management System · Spring 2026 · GIU
IBRAHIM MADANY · PROJECT MANAGER
§ 01 · SCOPE BASELINE
What we will — and won't — build.
The fence around the work, plus the ground we're standing on.
01
IN SCOPE
—
Authentication & GIU login
—
Event listing & detail pages
—
Organizer event CRUD
—
RSVP with capacity & waitlist
—
Email + in-app notifications
—
Admin dashboard & reports
02
OUT OF SCOPE
—
Online payment / ticketing
—
Native mobile application
—
Public (non-GIU) events
—
AI-based recommendations
—
External CRM integration
—
Live-streaming features
03
ASSUMPTIONS
—
GIU provides hosting & test DB
—
All students hold valid GIU accounts
—
Organizers supply event details on time
—
Stable campus internet
04
CONSTRAINTS
—
Single-semester delivery window
—
No external budget — academic only
—
Team of five student members
—
Limited QA time vs scope

## Slide 6
06
Campus Event Management System · Spring 2026 · GIU
IBRAHIM MADANY · PROJECT MANAGER
§ 01 · METHODOLOGY
Why Agile, not Waterfall.
An evolving academic product needs feedback loops, not a big up-front spec.
Agile / Scrum.
SELECTED — TWO-WEEK SPRINTS × 3
—
Requirements will evolve as feedback from students and organizers arrives.
—
Stakeholders need visible progress every sprint, not at the end.
—
MVP ships incrementally: auth → events → RSVP → notifications → reports.
—
Retrospectives let a 5-person student team self-correct fast.
NOT CHOSEN
Waterfall.
—
Heavy up-front spec doesn't fit a student project.
—
Late integration risk for notifications & reporting.
—
No mid-project feedback loop.
—
Change requests are expensive.

## Slide 7
07
Campus Event Management System · Spring 2026 · GIU
IBRAHIM MADANY · PROJECT MANAGER
§ 01 · TIMELINE
Twelve weeks, end to end.
From kickoff to handover, one semester.
W01
W02
W03
W04
W05
W06
W07
W08
W09
W10
W11
W12
Initiation & Planning
W1–W2
Sprint 1 · Foundation
W3–W5
Sprint 2 · Engagement
W6–W8
Sprint 3 · Closure
W9–W11
Final Review & Closure
W12–W12

## Slide 8
08
Campus Event Management System · Spring 2026 · GIU
§ 02 · CHAPTER
SCRUM MASTER
Yassin Kassem
IN THIS SECTION
01
Scrum Master role & ceremonies
02
Sprint 1 — Foundation + Authentication
03
Sprint 2 — Event creation + RSVP + Notifications
04
Sprint 3 — Reporting + QA + Deployment

## Slide 9
09
Campus Event Management System · Spring 2026 · GIU
YASSIN KASSEM · SCRUM MASTER
§ 02 · SCRUM CEREMONIES
The rhythm of the sprint.
Six recurring events keep the team aligned and the work honest.
01
Sprint Planning
START OF SPRINT
Pick backlog items, agree on goal & capacity.
02
Daily Standup
EVERY WEEKDAY
15 min — done, doing, blockers.
03
Backlog Refinement
MID-SPRINT
PO clarifies stories; team re-estimates.
04
Sprint Review
END OF SPRINT
Demo working increment to stakeholders.
05
Retrospective
END OF SPRINT
What worked, what to change. 2 actions.
06
Blocker Removal
CONTINUOUS
SM unblocks and keeps the board flowing.

## Slide 10
10
Campus Event Management System · Spring 2026 · GIU
YASSIN KASSEM · SCRUM MASTER
§ 02 · SPRINT 01 · FOUNDATION
Sprint 01 — Foundation.
Goal: Deliver working MVP — authentication + event listing.
ID
TASK
OWNER
HRS
STATUS
S1-01
Repository, branching strategy & CI skeleton
Ibrahim Madany
6
Done
S1-02
Database schema (users / events / RSVPs)
Loay Waleed
8
Done
S1-03
Login & registration with GIU email validation
Yassin Kassem
10
Done
S1-04
Role-based access control matrix
Yassin Kassem
8
Done
S1-05
Event listing page with filters & search
Youssef Othman
10
In Progress
S1-06
Event detail page (read-only)
Malek Khaled
6
In Progress
S1-07
Unit tests for auth & listing endpoints
Youssef Othman
6
To Do
S1-08
Sprint review & retrospective
Yassin Kassem
2
To Do

## Slide 11
11
Campus Event Management System · Spring 2026 · GIU
YASSIN KASSEM · SCRUM MASTER
§ 02 · SPRINT 02 · ENGAGEMENT
Sprint 02 — Engagement.
Goal: Event creation, RSVP and notifications working end-to-end.
ID
TASK
OWNER
HRS
STATUS
S2-01
Organizer event creation form & validation
Loay Waleed
10
Planned
S2-02
Event editing & cancellation flows
Loay Waleed
8
Planned
S2-03
RSVP / register button with feedback
Youssef Othman
8
Planned
S2-04
Capacity limit & waitlist logic
Malek Khaled
10
Planned
S2-05
Email notification service integration
Ibrahim Madany
10
Planned
S2-06
In-app notification feed
Youssef Othman
8
Planned
S2-07
Registration confirmation emails
Ibrahim Madany
5
Planned
S2-08
Integration tests: RSVP + notifications
Youssef Othman
8
Planned

## Slide 12
12
Campus Event Management System · Spring 2026 · GIU
YASSIN KASSEM · SCRUM MASTER
§ 02 · SPRINT 03 · CLOSURE
Sprint 03 — Closure.
Goal: Reporting engine + QA + deployment + handover.
ID
TASK
OWNER
HRS
STATUS
S3-01
Admin dashboard layout & KPIs
Ibrahim Madany
10
Planned
S3-02
Attendance & registration report queries
Loay Waleed
8
Planned
S3-03
Export data to CSV / PDF
Loay Waleed
6
Planned
S3-04
Security testing & dependency audit
Malek Khaled
8
Planned
S3-05
User Acceptance Testing with organizers
Youssef Othman
8
Planned
S3-06
Bug fixing & polish pass
Team
10
Planned
S3-07
Deployment to GIU / free-tier hosting
Ibrahim Madany
6
Planned
S3-08
Final handover documentation & demo
Team
5
Planned

## Slide 13
13
Campus Event Management System · Spring 2026 · GIU
§ 03 · CHAPTER
PRODUCT OWNER
Loay Waleed
IN THIS SECTION
01
Product vision & beneficiaries
02
Scope statement & scope creep control
03
Product backlog — prioritized user stories
04
Work Breakdown Structure (WBS)

## Slide 14
14
Campus Event Management System · Spring 2026 · GIU
LOAY WALEED · PRODUCT OWNER
§ 03 · PRODUCT VISION
A single home for everything happening on campus.
“
Give GIU a unified web platform where students discover and join events in seconds, organizers run them with zero spreadsheets, and admins see campus engagement at a glance.
STUDENTS
Discover events, RSVP in one click, get reminders.
ORGANIZERS
Create events, manage capacity, communicate updates.
ADMINS
Monitor engagement KPIs and pull reports.

## Slide 15
15
Campus Event Management System · Spring 2026 · GIU
LOAY WALEED · PRODUCT OWNER
§ 03 · SCOPE STATEMENT & CREEP CONTROL
Lock the baseline. Control change with discipline.
What we ship, what we don't, and how we say 'no' to mid-sprint additions.
01
IN SCOPE
Authentication
GIU login & roles
Event Module
Listing, detail, CRUD
RSVP
Capacity + waitlist
Notifications
Email + in-app
Dashboard
Admin KPIs & reports
02
OUT OF SCOPE
Payments
No ticketing
Mobile native
Web MVP only
Public events
GIU community only
AI recs
Not in MVP
External CRM
Manual exports only
03
CREEP CONTROL
Change Request
Written submission first
Impact Assessment
Time/cost/risk evaluated
Sponsor Approval
Instructor sign-off only
Sprint Lock
Backlog frozen mid-sprint
WBS Baseline
Not in WBS = not in project

## Slide 16
16
Campus Event Management System · Spring 2026 · GIU
LOAY WALEED · PRODUCT OWNER
§ 03 · PRODUCT BACKLOG
Ten user stories that shape the MVP.
Prioritized by value to the user, sized in story points, mapped to a sprint.
ID
USER STORY
PRIORITY
PTS
SPRINT
US-01
As a student, I want to log in with GIU credentials so my identity is verified.
High
5
S1
US-02
As a student, I want to browse upcoming events with filters.
High
8
S1
US-03
As a student, I want to view full event details before joining.
High
3
S1
US-04
As an organizer, I want to create events with date, capacity and description.
High
8
S2
US-05
As a student, I want to RSVP and see confirmation immediately.
High
5
S2
US-06
As an organizer, I want to edit or cancel an event and notify attendees.
Med
5
S2
US-07
As a student, I want email + in-app reminders before an event.
Med
8
S2
US-08
As an admin, I want a dashboard showing top events and attendance.
High
8
S3
US-09
As an admin, I want to export an attendance report (CSV/PDF).
Med
5
S3
US-10
As an admin, I want to deactivate misuse accounts to keep data clean.
Low
3
S3

## Slide 17
17
Campus Event Management System · Spring 2026 · GIU
LOAY WALEED · PRODUCT OWNER
§ 03 · WORK BREAKDOWN STRUCTURE
The work, decomposed.
Three branches. Each branch ships a baseline of deliverables.
0.0 Campus Event Mgmt
1.0 Initiation & Planning
1.1 Charter
1.2 Stakeholder Register
1.3 Risk Register
1.4 Sprint Plans
2.0 System Development
2.1 Authentication
2.2 Event Module
2.3 RSVP Module
2.4 Notifications
2.5 Reporting
3.0 Testing & Deployment
3.1 Unit Testing
3.2 Integration Testing
3.3 UAT
3.4 Deployment
3.5 Handover

## Slide 18
18
Campus Event Management System · Spring 2026 · GIU
§ 04 · CHAPTER
RISK MANAGER
Malek Khaled
IN THIS SECTION
01
Risk management overview & metrics
02
Risk register — seven risks scored
03
Probability–Impact matrix
04
Risk response strategy

## Slide 19
19
Campus Event Management System · Spring 2026 · GIU
MALEK KHALED · RISK MANAGER
§ 04 · RISK MANAGEMENT
See problems before they happen.
“Identify risks before they become issues.”
7
RISKS IDENTIFIED
Across product, team and infra
3
RED-ZONE RISKS
Active mitigation in progress
Sprint
REVIEW CADENCE
Re-scored at end of each sprint

## Slide 20
20
Campus Event Management System · Spring 2026 · GIU
MALEK KHALED · RISK MANAGER
§ 04 · RISK REGISTER
Seven risks. Three on active mitigation.
Score = Probability × Impact, reviewed at the end of every sprint.
ID
RISK
PROB.
IMPACT
SCORE
OWNER
MITIGATION
R1
Low student adoption of platform
Med
High
6
Product Owner
Awareness campaign, easy onboarding.
R2
Notification service failure
Med
High
6
PM / Dev
Retry queue, fallback to email, monitoring.
R3
Scope creep mid-sprint
High
Med
6
PM
Locked sprint backlog, formal CR process.
R4
Team member unavailability
Med
Med
4
Scrum Master
Pair work, shared docs, cross-skilling.
R5
Data privacy / PII issue
Low
High
3
Risk Manager
RBAC, encryption, minimal data collected.
R6
Hosting / deployment delay
Med
Med
4
PM
Free-tier backup host, early deploy spike.
R7
Organizer resistance to new tool
Med
Med
4
Comms Lead
Demo sessions, organizer feedback loop.

## Slide 21
21
Campus Event Management System · Spring 2026 · GIU
MALEK KHALED · RISK MANAGER
§ 04 · PROBABILITY × IMPACT
Where each risk sits today.
A 3×3 grid that drives the response strategy on the next page.
PROBABILITY
High
Med
Low
Low
Med
High
IMPACT
R3
R4 R6 R7
R1 R2
R5
LEGEND
Accept
Monitor only
Monitor
Review each sprint
Mitigate
Immediate action
TOP-3 ACTIVE
R1 — Adoption R2 — Notifications R3 — Scope creep

## Slide 22
22
Campus Event Management System · Spring 2026 · GIU
MALEK KHALED · RISK MANAGER
§ 04 · RISK RESPONSES
Four strategies. Seven risks.
Each risk is matched to the right action — not all risks deserve mitigation.
01
AVOID
ELIMINATE THE CAUSE ENTIRELY.
—
R5 Collect minimal PII to remove privacy exposure.
02
MITIGATE
REDUCE PROBABILITY OR IMPACT.
—
R1 Adoption campaign & onboarding
—
R2 Retry queue + monitoring
—
R3 Locked sprint backlog & CR process
03
TRANSFER
SHIFT THE RISK TO ANOTHER PARTY.
—
R6 Rely on managed hosting / free-tier SLA
04
ACCEPT
LIVE WITH IT; HAVE A CONTINGENCY.
—
R4 Pair work / cross-skilling
—
R7 Organizer feedback loop

## Slide 23
23
Campus Event Management System · Spring 2026 · GIU
§ 05 · CHAPTER
COMMS & QA LEAD
Youssef Othman
IN THIS SECTION
01
Stakeholder analysis & power–interest matrix
02
Team roles & collaboration tools
03
Communication plan
04
Definition of Done & quality
05
Lessons learned & project closure

## Slide 24
24
Campus Event Management System · Spring 2026 · GIU
YOUSSEF OTHMAN · COMMS & QA LEAD
§ 05 · STAKEHOLDERS
Power × Interest.
Who to manage closely, who to keep informed — at a glance.
POWER
High
Low
INTEREST →
KEEP SATISFIED
IT Department
Course Instructor
MANAGE CLOSELY
University Admins
Event Organizers
MONITOR
General Campus Staff
KEEP INFORMED
Students
STAKEHOLDER REGISTER
Students
End users
Easy discovery & RSVP
In-app updates
Event Organizers
Power users
Reliable tools, fast support
Bi-weekly demos
University Admins
Sponsor
Engagement KPIs, compliance
Milestone reviews
IT Support
Hosting / infra
Secure deployment
Architecture reviews
Course Instructor
Academic sponsor
On-time, quality delivery
Weekly status emails

## Slide 25
25
Campus Event Management System · Spring 2026 · GIU
YOUSSEF OTHMAN · COMMS & QA LEAD
§ 05 · TEAM ROLES & TOOLS
Five members. One stack.
Who owns what — and the lightweight tools that keep us aligned.
ROLES
MEMBER
ROLE
OWNS
Ibrahim Madany
Project Manager
Charter, timeline, integration
Yassin Kassem
Scrum Master
Ceremonies, blockers
Loay Waleed
Product Owner
Backlog, user stories
Malek Khaled
Risk Manager
Register, matrix, mitigation
Youssef Othman
Comms & QA Lead
Stakeholders, DoD, closure
STACK
Trello / Jira
Backlog & sprint board
GitHub
Version control & PRs
Google Drive
Docs & charter
WhatsApp / Slack
Day-to-day chat
Google Meet
Standups & reviews
Figma
UI mockups & review

## Slide 26
26
Campus Event Management System · Spring 2026 · GIU
YOUSSEF OTHMAN · COMMS & QA LEAD
§ 05 · COMMUNICATION PLAN
Right info, right channel, right cadence.
Daily internal syncs, weekly external reports, formal sprint reviews.
AUDIENCE
INFORMATION
METHOD
FREQUENCY
Team members
Sprint tasks, blockers
WhatsApp + Trello
Daily
Scrum Master
Standup updates
Google Meet
Daily
Product Owner
Backlog & demos
Sprint review
End of sprint
Instructor
Progress & risks
Email + status doc
Weekly
University Admin
Milestone summary
Presentation
Per milestone
Event Organizers
Feature demos
Demo session
Bi-weekly
Students
Platform updates
In-app + email
Per release

## Slide 27
27
Campus Event Management System · Spring 2026 · GIU
YOUSSEF OTHMAN · COMMS & QA LEAD
§ 05 · QUALITY
Definition of Done.
A story is only 'Done' when all six checks pass.
01
Code Reviewed
Peer reviewed and approved.
02
Acceptance Criteria
All AC demonstrably met.
03
Unit Tested
Tests added/updated, all green.
04
Integrated
Works end-to-end with related modules.
05
Documented
Docs and notes updated.
06
PO Accepted
Product Owner formally accepts.
QA LAYERS
Unit · Integration · UAT · Security & privacy · Performance · Docs review

## Slide 28
28
Campus Event Management System · Spring 2026 · GIU
YOUSSEF OTHMAN · COMMS & QA LEAD
§ 05 · LESSONS & CLOSURE
Lessons learned. Plane landed.
What we'd tell the next team on day one — and how we wrap.
LESSONS
01
Lock sprint scope clearly — changes mid-sprint cost more than they save.
02
Validate notification requirements early; spike it in Sprint 1.
03
Frequent stakeholder feedback catches gaps before they ship.
04
Document decisions from day one with short ADR-style notes.
05
Test role permissions early — RBAC bugs surface late and are painful.
CLOSURE CHECKLIST
✓
Final presentation delivered
✓
All deliverables reviewed vs WBS
✓
Lessons learned documented
✓
Stakeholder sign-off recorded
✓
Team formally released
✓
Handover package archived

## Slide 29
GIU · SPRING 2026
Thank
you.
Questions & discussion.
TEAM
Ibrahim Madany · Yassin Kassem · Loay Waleed · Malek Khaled · Youssef Othman
DR. ABDALLAH OSMAN